CyberShake Study 22.12
Technical Readiness Review
Scott Callaghan
Southern California Earthquake Center

---
Study 22.12 Technical Goals
Perform computationally largest CyberShake study to date
Use job bundling to improve queue times for SGT and post-processing jobs
Improve upon high-water mark of 46% of Summit
04/11/2023

---
Study 22.12 Scientific Goals
Perform an updated Broadband CyberShake calculation in Southern California, using BBP codes.
Calculate CyberShake results with a modified velocity model.
Merged taper model, using CVM-S4.26.M01 with the Ely-Jordan taper to 700m
Use an updated version of the Graves & Pitarka rupture generator
V5.5.2, same as is used in the BBP v22.4
Includes sampling of variability in rupture velocity
Denser hypocentral spacing (4.5 km to 4 km) → 31% more variations

---
Proposed Study sites
Same 335 sites as were used in Study 21.12
Site calculation order:
Standard 10 (USC, PAS, LADT, LBP, WNGC, SABD, SBSM, FFI, CCP, SMCA)
20 km grid
10 km grid
Additional POIs
5 km grid sites

---
Study 22.12 Data Products
Two-component seismograms (626k/site x 335 sites x 2 = 420 million)
Intensity measures
Deterministic
RotD50 and 100 at 25 periods (1-10 sec) + PGV: 2, 3, 4, 5, 7.5, and 10 sec stored in DB
Stochastic
RotD50 and 100 at 66 periods (0.01-10 sec) + PGA, PGV: 19 periods, PGA, PGV stored in DB
Duration metrics
Energy integral, Arias intensity, cumulative absolute velocity
Significant durations (5-75%, 5-95%, 20-80%) for velocity and acceleration: acceleration 5-75% and 5-95% for X and Y stored in DB
Hazard curves for 335 sites (0.1, 0.2, 0.5, 1, 2, 3, 4, 5, 7.5, 10 sec)
RotD50 hazard maps at 0.1, 0.2, 0.5, 1, 2, 3, 5, and 10 sec

---
Study 22.12 Parameters
1 Hz deterministic
100 m grid spacing
dt = 0.005 sec
SGT nt = 40000 timesteps (200 sec); 60000 timesteps/300 sec if any source-to-hypocentral distances are greater than 450 km
Seismogram nt = 8000 timesteps (400 sec)
50 Hz stochastic
Seismogram nt = 40000 timesteps (400 sec)
UCERF 2 ERF
Graves and Pitarka (2022) rupture generator

---
Changes to SGT Workflow Software Stack
Velocity mesh generation
UCVM 22.7.0
Implemented option for merged taper model
Modified implementation of minimum values
SGT code
Te-Yang’s kernel update applied to ensure reproducibility

---
Changes to PP Workflow Software Stack
DirectSynth post-processing code
Added OpenMP implementation
Support for passing in random seed and rupture velocity
Broadband code
CyberShake now links to BBP object files for consistency
Merge approach modified
Rupture generator
Updated to v5.5.2 and optimized

---
Changes to Workflows
SGT and DirectSynth jobs will be bundled to reduce queue times
Bin 2 jobs (922-2764 nodes) get +10 day aging boost
Bundles of 14 SGT jobs (938 nodes) x 40 minutes
Bundles of 10 DS jobs (1000 nodes) x 10 hours
Other jobs run using rvGAHP, with daemon running on dtn36
Use default pegasus-transfer to manage Globus Connect transfers
Pegasus v5.0.3
HTCondor v9.1.0

---
Computational Requirements
SGT workflow
78.8 node-hrs/site x 335 sites + 10% extra = 29k node-hours
Deterministic PP workflow
8.6 hrs/site x 92 nodes x 335 sites + 10% extra = 292k node-hrs
About 1/3 more rupture variations per site than previous studies
Stochastic PP workflow
8.8 hrs/site x 92 nodes x 335 sites + 10% extra = 297k node-hrs
High-frequency code is longer-running than in previous BB studies
Currently 285k node-hours available on Summit

---
Computational Plan
Unsure if OLCF will permit allocation overrun, as they have previously
Perform 20-site stress test of all 3 phases: 33.6k node-hours
Calculate SGTs for remaining 315 sites (24.8k node-hours)
Calculate low-frequency post-processing for remaining 315 sites (249.2k node-hours) – this comes to ~20k node-hours over allocation
Best to calculate this entirely on Summit, so SGTs don’t have to be transferred.
While study is going, establish broadband capability on Frontera
If OLCF cuts us off, run broadband calculations on Frontera
375k node-hours (828k available)

---
Storage Requirements
Summit (learned from Study 21.12 that no quotas are enforced on scratch)
507 TB SGTs
553 TB temporary data
73 TB output data
CARC
73 TB output files to project storage
66 TB free; will migrate additional pre-Study 15.4 data to OLCF HPSS
Database on moment.usc.edu
654 GB (7.1 billion rows)
Moment has 379 GB on disk + 846 GB in database free
Shock-carc workflow submission host
737 GB workflow logs (1.5 TB free)

---
Estimated Duration
At Study 21.12 throughput rates:
116 days to use up Summit allocation
252 days to finish study
Anticipate higher throughput on Summit due to job bundling
At Study 21.12 percentage of system usage, 88 days to complete broadband calculations on Frontera
Overall estimated duration of 90 days on Summit + 88 days on Frontera with 30 days overlap = 150 days.

---
Risks
Storage on Summit
~460 TB for SGTs for 315 sites
May need to temporarily store them elsewhere (OLCF HPSS, CARC scratch, TACC Ranch)
Storage on CARC
Plan to migrate more data to OLCF HPSS (can move ~1.5 TB/day)
After study completes, investigate data compression for seismograms
Limited compute time on Summit
Move calculations to Frontera
Additional resources include CARC, Expanse, Perlmutter, Delta
Reduced support during holidays
Dependency on moment

---
Action Items
Tag code in github repo
Test Pegasus with Globus file transfer (with v5.0.3)
Notify OLCF contact of plans, and request additional bin 5 jobs